# Shopping Copilot

Business proposal for an apparel shopping assistant

SMYA  |  English edition  |  27 September 2026

# 01  Executive summary

Shopping Copilot is a product selection assistant for small and medium-sized apparel retailers. We propose a controlled pilot within one retailer’s limited catalog, helping shoppers turn an imprecise need into an evidence-backed shortlist while reducing repetitive product searches, comparisons and preference clarification by service staff. The first priority is faster selection, lower manual workload and accurate product information; sales growth is a commercial hypothesis to validate through an experiment.

## Business problem and proposed response

Shoppers repeatedly move between search results, product pages and service conversations. Changing color, material or budget can require them to explain their needs again. Shopping Copilot combines conversation, product results, a requirements summary and comparison of up to three saved products. It separates requirements, preferences and exclusions, supports revisions and undo, and explains recommendations and unknowns using catalog evidence. The shopper confirms the final selection. [S2–S5]

## Proposed pilot decision

Approve an eight-week staged pilot: two weeks for baseline and data preparation, two weeks for deployment hardening, and four weeks of limited-traffic evaluation. The planning allowance is S$3,500 for setup and up to S$600 per month for operations. Reserving two months of operating costs gives a total authorization ceiling of S$4,700. These are planning assumptions requiring owner approval against actual quotations and effort. Public traffic is conditional on acceptance of real data, human assistance, security controls and rollback capability.

## Expected outcomes and current maturity

Pilot targets are a reduction in median time to a usable shortlist from an assumed 10 to 6 minutes, a 40% reduction in staff hours for repetitive selection enquiries, and 98% evidence accuracy for sampled objective product claims. Improving conversion from 3.0% to 3.3% is a longer-term validation target, not an achieved result. The code supports an end-to-end demonstration, but the local demo catalog contains only 15 synthetic products. Real search assets, production deployment and transaction attribution remain to be completed. Confirming a selection records a decision within the session; it does not place or pay for an order. [S3–S8]

# 02  Problem and opportunity

## Target business and stakeholders

The initial use case is a Singapore-based apparel SME serving online shoppers in English. The pilot starts with categories such as dresses and T-shirts, using retailer-authorized product information. The business owner cares about sales and operating costs; service staff about handling time and repeated explanations; merchandising staff about attributes, prices and inventory quality; and shoppers about understanding differences and making a reliable choice. This is a pilot business profile, not evidence of a signed customer or completed interviews.

## Repeated work in the current journey

After a keyword search, the shopper opens individual pages and manually compares material, fit and price. Uncertainty leads to a service enquiry. Staff repeat questions about needs, consult product records and assemble options. A changed requirement can restart that work. The potential consequences are capacity constrained by staff time, interrupted purchase decisions and inconsistent descriptions across employees. The pilot will establish whether these frictions exist rather than presume a measured revenue loss.

| Baseline assumption | Value | Validation method |
| --- | --- | --- |
| Eligible website sessions per month | 10,000 | Analytics excluding bots and internal traffic |
| Repetitive selection enquiries per month | 600 | Ticket classification and sample review |
| Staff handling time per enquiry | 6 minutes | Timed observation including follow-up |
| Median time to usable shortlist | 10 minutes | Matched user tasks |
| Purchase conversion / order value | 3.0% / S$55 | Linked retailer order and session data |

Under these assumptions, repetitive enquiries consume 60 staff hours per month. Recovered time could support complex presales and aftersales work without reducing headcount. During weeks 1–2, interview the owner, two service staff and 5–8 shoppers, and review at least 100 enquiries. Replace the assumptions with measured baselines before confirming pilot economics.

# 03  Solution and shopper journey

Shopping Copilot organizes product selection as a revisable, explainable conversation. It chooses whether to clarify, retrieve, answer a product question, compare or update the shortlist according to session state; not every message triggers another search. The implementation combines rules, structured state and retrieval tools. Model assistance is optional and off by default, so the prototype should not be described as an autonomous sales agent using a generative model on every turn. [S3–S6]

| Step | Shopper experience and system behavior |
| --- | --- |
| 1 Express a need | For example, “I need a blue dress. I prefer cotton.” The assistant separates explicit requirements from preferences and shows the recorded needs. |
| 2 Review and clarify | Show candidates and supporting evidence; ask a bounded clarification when useful. Unlisted information remains unknown. |
| 3 Revise and refine | Revise requirements, hide an item, request more options or undo a change; review the updated requirements before continuing. |
| 4 Save and compare | Save up to three products within the session; the frontend comparison button becomes available with at least two saved options. Review attributes and evidence. |
| 5 Confirm a decision | The shopper confirms. Later preference or shortlist changes can invalidate confirmation and require review. Transactions remain in the retailer’s existing process. |

## Scope and subsequent work

Existing scope includes session-level requirements, a catalog-search adapter, evidence displays, product details, saving, comparison, confirmation and a backend audit endpoint. Pilot work adds real catalog data, same-origin API routing, protected deployment, human assistance and business-event/order attribution. Accounts, cross-session preferences, multiple retailers and additional categories can follow later. Current scope does not promise live web-wide price comparison, stock reservation, guaranteed fit, payment, refunds or autonomous ordering. [S2–S8]

# 04  Business value and adoption

| Value | How value is created | Outcome to measure |
| --- | --- | --- |
| Productivity | Reuse session preferences and candidates to reduce repeated questions and page checking | Staff minutes per completed selection task |
| Service | Revise needs, inspect evidence and compare within one journey | Time to shortlist and satisfaction |
| Revenue opportunity | Help shoppers resolve uncertainty and proceed to the existing purchase journey | Purchase conversion by group and incremental gross profit |
| Risk control | Keep unknowns explicit and recheck decisions after changes | Factual error rate and misleading claims |
| Scale | Separate catalog maintenance from enquiry handling and reuse workflow/data standards | Peak service quality and cost per session |

## Differentiation and alternatives

Standard filters serve shoppers with precise criteria; human staff handle complex and exceptional cases; FAQ tools answer fixed policy questions. Shopping Copilot targets the stage between an uncertain need and an explainable shortlist by retaining current requirements, supporting changes of mind and showing evidence. The pilot compares it with the retailer’s existing search and service journey rather than assuming superiority over every alternative. Better filters may be more economical when catalog attributes are sparse or needs are simple.

## Adoption and future commercialization

Begin as a single-retailer website component or dedicated selection page, with staff training and an exception process. Assign one business owner for outcomes, one merchandising owner for data and one technical owner for service quality, with weekly feedback reviews. After value is demonstrated, consider a managed subscription with a usage allowance for other SMEs. Pricing must cover onboarding, operations and support and be validated through willingness-to-pay interviews. No subscription revenue is assumed at this stage, and paid placement is not part of relevance ranking.

# 05  Impact metrics and validation design

These are proposed targets. Definitions, denominators and exclusions must be fixed before the pilot begins. Passing software tests does not establish achievement of business KPIs. [S9]

| Metric and owner | Baseline to target | Measurement definition |
| --- | --- | --- |
| Time to shortlist / Product owner | Assumed 10 → 6 minutes | From initial need to at least two candidates meeting verified hard requirements; also report task completion to avoid survivor bias |
| Manual workload / Service lead | Assumed 60 → 36 hours/month | Normalize for enquiry volume and mix; include escalations and rework |
| Evidence accuracy / Merchandising | Measure baseline → ≥98% | Review at least 200 checkable claims; fraction both correct and supported |
| Purchase conversion / Business owner | Assumed 3.0% → 3.3% | Purchasing sessions / eligible randomized sessions; +0.3 percentage points, or +10% relative |
| Satisfaction and reliability / Product and Tech | CSAT ≥4/5; p95 ≤10 seconds | Report survey response rate; ≥99% successful interactions, plus errors and unknown-data rates |

## Experiment and attribution

Take 20% of eligible traffic for the pilot and randomize it between the existing journey and a journey with assistant access, keeping assignments stable. Analyze by initial assignment, retaining non-users in the treatment denominator. Add pseudonymous experiment IDs and search, comparison, confirmation, escalation and purchase events. Purchases must come from the retailer’s order system; shortlist confirmation is not a purchase. In weeks 1–2, use at least 20 shoppers for counterbalanced task testing and report time medians and distributions.

At 10,000 eligible sessions per month, the four-week pilot yields about 1,000 sessions per arm, generally insufficient to detect a change from 3.0% to 3.3%. A two-sided 5% test with 80% power and independent observations requires approximately 53,000 sessions per arm; repeat visitors may increase the requirement. The four-week decision therefore prioritizes workflow quality and safe operation. Report conversion intervals and direction, then extend sampling before claiming revenue impact.

# 06  Budget and economics

The following monthly scenarios assume one retailer and full coverage of eligible traffic, in Singapore dollars. They are not a forecast of pilot revenue: the pilot has limited traffic while setup and operating costs still occur. Assumptions are a loaded staff cost of S$25/hour, S$55 order value and 40% merchandise gross margin. Additional marketing, payment, returns and other variable expenses are not yet deducted.

| Budget item | Planning allowance |
| --- | --- |
| One-time implementation: 100 hours × S$25 | S$2,500 |
| Data preparation, acceptance and training: 24 hours × S$25 | S$600 |
| One-time contingency | S$400 |
| Total one-time budget | S$3,500 |
| Monthly compute and storage / model allowance / monitoring / maintenance | S$200 / 150 / 100 / 150 |
| Total monthly operating budget | S$600 |

Base case: released time = 600 enquiries × 6 minutes ÷ 60 × 40% = 24 hours, worth S$600 in capacity. Incremental orders = 10,000 × (3.3% − 3.0%) = 30; incremental sales are S$1,650 and merchandise gross profit is S$660. Monthly net benefit including capacity is 600 + 660 − 600 = S$660. The simple economic payback on setup is about 5.3 months.

| Scenario | Workload cut / conversion | Monthly net incl. capacity | Monthly net, unchanged payroll |
| --- | --- | --- | --- |
| Conservative | 20% / 3.0% | −S$300 | −S$600 |
| Base | 40% / 3.3% | S$660 | S$60 |
| Upside | 50% / 3.6% | S$1,470 | S$720 |

With unchanged payroll, S$600 of capacity is not cash saved. The base case leaves only S$60/month toward setup, implying about 58.3 months of simple payback before omitted expenses, which would reduce returns further. Covering S$600 of operating cost through incremental gross profit alone requires about 28 additional orders, or a 0.28-percentage-point conversion increase. Expansion should depend on usable recovered capacity and validated profit, not treating theoretical capacity as cash.

# 07  Technical feasibility and scaling

## Existing architecture and data flow

The React/TypeScript frontend calls a Python service through same-origin JSON APIs. Conversation handling updates session state and distinguishes requirements, preferences and exclusions. The real-search path uses an adapter for BM25 retrieval and local sequence-classification reranking, followed by requirement matching and evidence presentation. Details and shortlist comparison reuse catalog records; optional model assistance supports explanations and comparison. Model credentials belong only on the backend. [S2–S6]

The frontend consumes six endpoints: health, session creation, chat, selection, product detail and comparison. A separate backend audit endpoint is not called by the frontend. Sessions are in memory, with a default limit of 128 and an idle lifetime of 3,600 seconds; refreshing the page creates a new session. These are prototype state-management settings, not evidence of capacity for 128 concurrent users. [S2–S3]

## Prerequisites for a real pilot

First, the merchandising owner supplies an authorized catalog with stable IDs, categories, attributes, descriptions, price currency and data timestamps, with explicit sources for variants, inventory and price. The current real-search adapter sets price and ratings to null; changing the frontend label cannot supply real prices. Data and mappings need expansion. Version the index with its product table and supply matching reranker weights. A successful health check must be followed by acceptance of real queries. [S4, S7]

Second, configure same-origin production routing: the development proxy serves local integration, while the static Worker does not forward API requests. Move the demo HTTP service to a production-capable architecture with identity/session ownership checks, rate limits, shared session storage, timeouts and monitoring. The single-threaded service and global lock constrain throughput; adding frontend instances does not solve this. Multiple backend instances require per-session coordination and appropriate handling of storage-connection thread constraints. [S3, S8]

## Cost and capacity management

Validate catalog and state behavior with model assistance off, then use matched tasks to assess whether model assistance improves quality. Record tokens, latency and cost per call; multistage comparison must fit within the frontend’s 45-second timeout. Load-test at twice the retailer’s measured peak before increasing traffic in stages. New categories require updated schemas and acceptance samples; multiple retailers require tenant isolation, separate data permissions and retailer-level metering. These are subsequent implementation requirements.

# 08  Risk management and human oversight

Automation is bounded to helping the shopper form an informed choice. The shopper retains decision authority; the retailer remains responsible for product facts, special commitments, transactions and exceptions. The existing confirmation step is shopper confirmation, not staff approval, live-agent transfer or integration with a service ticket. [S2–S3]

| Risk | Existing control | Control to add before pilot |
| --- | --- | --- |
| Incorrect or excessive claims | Evidence and unknown states; comparison separate from confirmation | Fact sampling; no personal-fit guarantee; suspend affected features after serious misleading claims |
| Stale or missing data | Fallback for unknown prices and ratings | Assign refresh ownership/cadence, label stale values and confirm in the commerce system |
| Lost state or repeated actions | Serialized frontend requests, no automatic POST replay, bounded sessions | Shared state, version checks, idempotency and post-timeout status lookup |
| Privacy and unauthorized access | Backend-only model secrets; operations limited to products shown in-session | Session ownership, data minimization, redacted logs, access control and retention limits |
| Malicious text or model failure | Bounded tool scope; model-off operation | Treat catalog/input as untrusted data; adversarial tests, rate limits and safe fallback |

## Human assistance workflow

Add a clear “Contact a person” route before the pilot. Triggers include an explicit request, failure after two clarification attempts, unverifiable hard requirements, conflicting product data and out-of-scope order, payment or return questions. With the shopper’s confirmation, send only the necessary requirements summary, candidate products and unresolved questions to staff; do not default to a full transcript or sensitive data. Propose a 15-minute first response during staffed hours and display actual hours otherwise. This route, routing logic and service commitment need implementation and acceptance; live handoff is not present in the current code.

The technical owner monitors errors, p95 latency, session cost and data freshness; merchandising reviews recommendation evidence weekly; the business owner controls suspension and expansion. Unauthorized data access, unintended transaction execution or serious misleading claims trigger immediate suspension of the affected function and fallback to the existing journey, retaining necessary incident evidence.

# 09  Implementation plan and acceptance

| Stage | Work and owner | Gate to proceed |
| --- | --- | --- |
| Weeks 1–2 Baseline and data | Business: enquiry/sales baseline. Merchandising: authorized catalog. Product: interviews and task tests. | Agreed category, field coverage, sources and measured baseline; revised budget and KPIs |
| Weeks 3–4 Pilot hardening | Tech: search assets, routing, session protection, monitoring and events. Service: human assistance. | Real-query and end-to-end acceptance; timeout, access, unknown-data, rollback and human-help checks pass |
| Weeks 5–8 Controlled evaluation | Product: randomized allocation. Business: weekly workflow/cost review. Merchandising: evidence checks. | Quality, safety and cost gates met; conversion uncertainty reported; continue, revise or stop decision |
| Week 9 onward Conditional expansion | Increase traffic within measured capacity; continue conversion experiment and expand category by category | No degradation at added load; economics reassessed using observed data |

## Pilot acceptance criteria

Continue if median selection time reaches 6 minutes without lower completion than control; normalized manual workload falls 40%; evidence accuracy reaches 98%; no severe privacy, access or misleading-claim incident occurs; interaction success is at least 99%, p95 latency at most 10 seconds, and monthly operating cost at most S$600. If targets are missed, diagnose data, interface or model causes, revise and retest. A favorable metric cannot compensate for a severe risk.

## Handover and exit

Deliver a verified catalog/index version, deployment configuration, operating and staff-training guides, monitoring dashboard, metric definitions and pilot evaluation. The business owner approves each next stage; the technical owner must be able to disable assistant access and restore the original journey. If essential data, human assistance or security controls are not ready by week 4, retain internal demonstration mode and revise the schedule rather than expose the incomplete prototype to public traffic.

# 10  Demo script and evidence alignment

Use a 5–6 minute demo with one business story: helping a shopper form a trustworthy shortlist faster. Show the Demo catalog label and start a new conversation so pre-seeded results are not presented as real shopper actions. The current frontend is in English; the following inputs align with that interface. [S2, S3]

| Time | Action and display | Claim supported |
| --- | --- | --- |
| 0:00–0:40 | Show the existing search, page-review, enquiry and comparison journey; identify assumed baselines | Clear problem; no claim of measured savings yet |
| 0:40–1:30 | Enter “I need a blue dress. I prefer cotton.” Show products, Must have and Preferences | Structured needs and catalog recommendations |
| 1:30–2:20 | Change a color or preference, show the updated summary, then enter “Undo” | Visible, reversible requirement changes |
| 2:20–3:30 | Open details and evidence, save two products, compare, and reveal unlisted attributes | Evidence-backed comparison and disclosure of unknowns |
| 3:30–4:20 | Confirm the selection and show the no-order notice; remove one item and show confirmation invalidation | Shopper control and review after changes |
| 4:20–5:30 | Explain plans for the real catalog, human-help route and deployment; show KPIs and budget | A path from prototype to a measurable pilot |

## Boundaries of demo evidence

A timed demonstration can show task steps, but one demo cannot establish a population-wide 40% time or workload reduction; that requires the pilot. With model assistance off, present catalog/rule-supported comparison rather than verified generative reasoning. Describe human transfer as planned work rather than simulate an integrated service. Some undo/redo buttons are unavailable in particular UI states; use chat commands where needed during the demo and fix and recheck these controls before a public pilot. [S2, S8]

# 11  Evidence and assumption register

References identify the current local project copy, reviewed and tested on 27 September 2026. S1 defines the evaluation dimensions; S2–S8 support capability and technical-status statements; S9 records this verification scope. Business baselines, budgets and growth figures are assumptions or targets, not customer results.

S1  SMYA - business proposal guidelines.pdf
Pages 3–10: problem/opportunity, value, impact, feasibility/scalability, proposal quality and demo alignment.

S2  toc-frontend/src/{App,useShopping,components,Overlays,api,contracts,model}.ts*
UI, six APIs, 45-second timeout, save/compare, confirmation semantics and missing-data display.

S3  work/source/agentic_workflow/mvp/server.py
Sessions, three-item limit, confirmation/invalidation, audit, memory limits and HTTP service.

S4  work/source/search_tool/tool.py; agentic_workflow/shopping_agent/search_adapter.py
BM25/local-model reranking, data mapping and null price/ratings; second path is under work/source.

S5  work/source/description_module/{pipeline.py,README.md}
Separation of objective/personalized comparison, evidence, unknowns and model-off fallback.

S6  work/source/agentic_workflow/{__main__.py,shopping_agent/model_provider.py}
Explicit demo mode, model-off default and local/cloud provider configuration.

S7  work/source/agentic_workflow/{preflight.py,search_resources.py}
Checks for product table, index, matching weights and dependencies; resources currently incomplete.

S8  toc-frontend/{README.md,vite.config.mjs,worker/index.js}
Deployment routing and integration limits; README findings cross-checked against relevant code.

S9  Verification in this review
Backend verify: 599 passed; description_module: 8 passed; frontend vitest: 12 passed; tsc passed. Real-search preflight did not pass.

Verification boundary: tests cover offline, simulated and interface behavior, not real-retailer data quality, live model quality, concurrent capacity or business returns. The first backend run was interrupted by local-port restrictions; the full rerun passed with local test binding allowed. Real search still lacks its table, index, weights and some dependencies. Historical live-search pass statements are not treated as proof that this copy can run live search.